## Schedule
ISD Application Group - 2019 YEAR END ACTIVITIES |  |  |  |  | - without ISD on-site | [18 empty] | Prepared By | Checked By | Confirmed By | Approved By
WORK SCHEDULE |  |  |  |  | - with ISD on-site
[24 empty] | Fred Baria | Geryl Mendoza | Naoki Kobayashi | Atsushi Hanazato
[24 empty] | AS5 | Section Head | Dept Head | Div Head
ITEM | DESCRIPTION | INCHARGE | Dec | [16 empty] | Jan
|  |  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4
| Electricity EPPI |  | P | P | P | P | P | P | P | X | X | X | X | X P | P | P | P | P | P | P | P | P | P
1 | Biometrics - Christmas Party
1.1 | Change to Biometrics time to 3:30PM @ 1330 | Mec/Von/Sybil(HR) | bar: Dec 21
1.2 | Change to Biometrics back to 5:00PM @ 1700 | Mec/Sybil(HR) | bar: Dec 21
2 | Production Schedule
2.1 | Printer | DS
NS
2.2 | VP | (No Plan)
2.3 | IPS and IBM | DS
NS
2.4 | F2IM and F3IM | DS
NS
2.5 | ISD Support | Rex | bar: Dec 28
2.6 | ISD Support | Mec | bar: Dec 30
3 | HRC - W2 Processing (Tax)
3.1 | Restore Live Env Backup to Test Env | Aldrin (6-2)
3.2 | W2 Processing (Day 1) | Aldrin (6-2)
3.3 | W2 Processing (Day 2) | Rex (6-2), Fred (7-4) | bar: Dec 28
3.4 | Tax Levelling and Checking | Eye (HR) / Niña (Legal) | bar: Dec 30
4 | Canteen Activity
4.1 | Configure IP Address of additional 3 PCs | Von | bar: Dec 20 to Dec 21
4.2 | Register in ADMIN System - Canteen PC Master | Mec (8-5) | bar: Dec 30
4.3 | Testing of Canteen Station PCs | Mec (8-5) | bar: Dec 30
5 | Server OS Migration Checking
5.1 | EPPISQL1
5.1.1 | - Migration | Erwin
5.1.2 | - Checking and Confirmation | Fred
5.1.3 | - First Run Support | Fred | bar: Dec 28
5.2 | EPPISQL1N1
5.2.1 | - Migration | Erwin
5.2.2 | - Checking and Confirmation | Fred
5.2.3 | - First Run Support | Fred | bar: Dec 28
5.3 | EPPISQL2
5.3.1 | - Migration | Erwin
5.3.2 | - Checking and Confirmation | Fred
5.3.3 | - First Run Support | Fred | bar: Dec 28
5.4 | VMEPPIQAITDB
5.4.1 | - Migration | Erwin
5.4.2 | - Checking and Confirmation | Aldrin
5.4.3 | - First Run Support | Fred | bar: Dec 28
5.5 | VMEPPIQAITWEB
5.5.1 | - Migration | Erwin
5.5.2 | - Checking and Confirmation | Aldrin
5.5.3 | - First Run Support | Fred | bar: Dec 28
5.6 | VMEPPIPARTSPROD
5.6.1 | - Migration | Erwin
5.6.2 | - Checking and Confirmation | Aldrin
5.6.3 | - First Run Support | Fred | bar: Dec 28
5.7 | VMEPPIPPWEB1
5.7.1 | - Migration | Erwin
5.7.2 | - Checking and Confirmation | Aldrin
5.7.3 | - First Run Support | Fred | bar: Dec 28
5.8 | VMEPPISHP1
5.8.1 | - Migration | Erwin
5.8.2 | - Checking and Confirmation | Fred
5.8.3 | - First Run Support | Fred | bar: Dec 28
5.9 | VMEPPISHPDB1
5.9.1 | - Migration | Erwin
5.9.2 | - Checking and Confirmation | Fred
5.9.3 | - First Run Support | Fred | bar: Dec 28
5.10 | VMEPPISHAREDB1
5.10.1 | - Stop Interface GNS+ | Erwin
5.10.2 | - Transfer Server | Erwin
5.10.3 | - Check and Confirm Programs | Fred
5.10.4 | - First Run Support | Fred | bar: Dec 28
5.11 | VMEPPIDWH1
5.11.1 | - Migration | Erwin
5.11.2 | - Checking and Confirmation | Fred
5.11.3 | - First Run Support | Fred | bar: Dec 28
5.12 | VMEPPITESTDB
5.12.1 | - Migration | Erwin
5.12.2 | - Checking and Confirmation | Fred
5.12.3 | - First Run Support | Fred | bar: Dec 28
5.13 | VMEPPIVPUGITDB
5.13.1 | - Migration | Erwin
5.13.2 | - Checking and Confirmation | Fred
5.13.3 | - First Run Support | Rex | bar: Dec 28
5.14 | VMEPPIVPUGITWEB
5.14.1 | - Migration | Erwin
5.14.2 | - Checking and Confirmation | Fred
5.14.3 | - First Run Support | Rex | bar: Dec 28
5.15 | VMEPPIAPPS7
5.15.1 | - Migration | Erwin
5.15.2 | - Checking and Confirmation | Fred
5.15.3 | - First Run Support | Rex | bar: Dec 28
6 | Ekanban Data Archive
6.1 | Data Archiving | Ogura san | bar: Dec 23 to Dec 24
6.2 | Confirmation of Data | Fred
7 | Business Control - BP1 Data Consolidation Support
7.1 | Budget Uploading Support | Fred
7.2 | Generation of Reports | Fred | bar: Jan 2
| Fred | Dec 27, 28 > Server Migration and HRC W2 Processing, Production Operation Startup Support
Jan 2 > BP1 Budget Consolidation - generationi of reports
| Aldrin | Dec 27 > Server Migration and HRC W2 Processing
| Rex | Dec 28 > HRC W2 Processing and Production Operation Support
| Mec | Dec 30 > Production Operation Support and F3 Canteen Relayout Support

## Printer_WorkSched
LINUS PROUCTION PLAN AND REWORK SKED
NEW PRODUCTION
|  |  | 2019-12-18 | 2019-12-19 | 2019-12-20 | 2019-12-21 | 2019-12-22 | 2019-12-23 | 2019-12-24 | 2019-12-25 | 2019-12-26 | 2019-12-27 | 2019-12-28 | 2019-12-29 | 2019-12-30 | 2019-12-31 | 2020-01-01 | 2020-01-02 | 2020-01-03 | 2020-01-04 | 2020-01-05 | 2020-01-06 | 2020-01-07 | 2020-01-08 | 2020-01-09 | 2020-01-10 | 2020-01-11 | 2020-01-12
Line | Shift | Mpr | 2019-12-18 | 2019-12-19 | 2019-12-20 | 2019-12-21 | 2019-12-22 | 2019-12-23 | 2019-12-24 | 2019-12-25 | 2019-12-26 | 2019-12-27 | 2019-12-28 | 2019-12-29 | 2019-12-30 | 2019-12-31 | 2020-01-01 | 2020-01-02 | 2020-01-03 | 2020-01-04 | 2020-01-05 | 2020-01-06 | 2020-01-07 | 2020-01-08 | 2020-01-09 | 2020-01-10 | 2020-01-11 | 2020-01-12
B40 | DS | B40 | 2019-12-19: 112; 2019-12-20: 140; 2019-12-21: 112; 2019-12-28: 112; 2019-12-30: 182; 2020-01-03: 112; 2020-01-04: 182
B40 | NS | B40 | 2019-12-18: 112; 2019-12-19: 112; 2019-12-20: 140; 2019-12-28: 168; 2019-12-30: 182; 2020-01-03: 182; 2020-01-04: 182
B40 | Total |  | 112 | 224 | 280 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 280 |  | 364 | 0 | 0 | 0 | 294 | 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cumm Total |  | 112 | 336 | 616 | 728 | 728 | 728 | 728 | 728 | 728 | 728 | 1008 |  | 1372 | 1372 | 1372 | 1372 | 1666 | 2030 | 2030 | 2030 | 2030 | 2030 | 2030 | 2030 | 2030
REWORK
|  |  | 2019-12-18 | 2019-12-19 | 2019-12-20 | 2019-12-21 | 2019-12-22 | 2019-12-23 | 2019-12-24 | 2019-12-25 | 2019-12-26 | 2019-12-27 | 2019-12-28 | 2019-12-29 | 2019-12-30 | 2019-12-31 | 2020-01-01 | 2020-01-02 | 2020-01-03 | 2020-01-04 | 2020-01-05 | 2020-01-06 | 2020-01-07 | 2020-01-08 | 2020-01-09 | 2020-01-10 | 2020-01-11 | 2020-01-12
Line | Shift | Mpr | 2019-12-18 | 2019-12-19 | 2019-12-20 | 2019-12-21 | 2019-12-22 | 2019-12-23 | 2019-12-24 | 2019-12-25 | 2019-12-26 | 2019-12-27 | 2019-12-28 | 2019-12-29 | 2019-12-30 | 2019-12-31 | 2020-01-01 | 2020-01-02 | 2020-01-03 | 2020-01-04 | 2020-01-05 | 2020-01-06 | 2020-01-07 | 2020-01-08 | 2020-01-09 | 2020-01-10 | 2020-01-11 | 2020-01-12
B32 | DS | B32 | 2019-12-19: Set-up; 2019-12-20: RW-D; 2019-12-21: RW-D; 2019-12-28: RW-D; 2019-12-30: RW-D; 2020-01-03: RW-D; 2020-01-04: RW-D; 2020-01-06: Louvre Prod'n
B32 | NS | B32 | 2019-12-19: Set-up; 2019-12-20: RW-D; 2019-12-28: RW-D; 2019-12-30: RW-D; 2020-01-03: RW-D; 2020-01-04: RW-D; 2020-01-06: Louvre Prod'n
B35 | DS | B35 | 2019-12-20: 28; 2019-12-21: 28; 2019-12-28: 56; 2019-12-30: 112; 2020-01-03: 140; 2020-01-04: 168; 2020-01-06: Louvre Prod'n
B35 | NS | B34 | 2019-12-20: 28; 2019-12-28: 56; 2019-12-30: 112; 2020-01-03: 140; 2020-01-04: 108; 2020-01-06: Louvre Prod'n
RW | Total |  | 0 | 0 | 56 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 112 |  | 224 | 0 | 0 | 0 | 280 | 276 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RW | Cumm Total |  | 0 | 0 | 56 | 84 | 84 | 84 | 84 | 84 | 84 | 84 | 196 |  | 420 | 420 | 420 | 420 | 700 | 976 | 976 | 976 | 976 | 976 | 976 | 976 | 976
New +RW | Total |  | 112 | 224 | 336 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 392 | 0 | 588 | 0 | 0 | 0 | 574 | 640 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New +RW | Cumm Total |  | 112 | 336 | 672 | 812 | 812 | 812 | 812 | 812 | 812 | 812 | 1204 |  | 1792 | 1792 | 1792 | 1792 | 2366 | 3006 | 3006 | 3006 | 3006 | 3006 | 3006 | 3006 | 3006
|  |  | 2019-12-18 | 2019-12-19 | 2019-12-20 | 2019-12-21 | 2019-12-22 | 2019-12-23 | 2019-12-24 | 2019-12-25 | 2019-12-26 | 2019-12-27 | 2019-12-28 | 2019-12-29 | 2019-12-30 | 2019-12-31 | 2020-01-01 | 2020-01-02 | 2020-01-03 | 2020-01-04 | 2020-01-05 | 2020-01-06 | 2020-01-07 | 2020-01-08 | 2020-01-09 | 2020-01-10 | 2020-01-11 | 2020-01-12
Line | Destination |  | 2019-12-18 | 2019-12-19 | 2019-12-20 | 2019-12-21 | 2019-12-22 | 2019-12-23 | 2019-12-24 | 2019-12-25 | 2019-12-26 | 2019-12-27 | 2019-12-28 | 2019-12-29 | 2019-12-30 | 2019-12-31 | 2020-01-01 | 2020-01-02 | 2020-01-03 | 2020-01-04 | 2020-01-05 | 2020-01-06 | 2020-01-07 | 2020-01-08 | 2020-01-09 | 2020-01-10 | 2020-01-11 | 2020-01-12
Ex-fact | Carson |  | 2020-01-04: 756
Ex-fact | Indy |  | 2019-12-21: 616; 2020-01-06: 784
Ex-fact | Total |  | 0 | 0 | 0 | 616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 756 | 0 | 784 | 0 | 0 | 0 | 0 | 0
| Cumm Total |  | 0 | 0 | 0 | 616 | 616 | 616 | 616 | 616 | 616 | 616 | 616 |  | 616 | 616 | 616 | 616 | 616 | 1372 | 1372 | 2156 | 2156 | 2156 | 2156 | 2156 | 2156
OB | Carson |  | 2020-01-08: 756
OB | Indy |  | 2019-12-25: 616; 2020-01-08: 784
OB | Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1540 | 0 | 0 | 0
| Cumm Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616 | 616 | 616 | 616 |  | 616 | 616 | 616 | 616 | 616 | 616 | 616 | 616 | 616 | 2156 | 2156 | 2156 | 2156
Allow
Stocks | Total |  | 112 | 336 | 672 | 196 | 196 | 196 | 196 | 196 | 196 | 196 | 588 | 588 | 1176 | 1176 | 1176 | 1176 | 1750 | 1634 | 1634 | 850 | 850 | 850 | 850 | 850 | 850 | 850 | 39.42%

## WBS
Project Name : |  | Holiday work schedule - 2019
Reference :
[7 empty] | 43814 | 0 | 0 | 0 | 0 | 0 | 0 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830 | 43831 | 43832 | 0 | 0 | 43835 | 0 | 0 | 0 | 0 | 0 | 43841
[7 empty] | 2019-12-15 | [6 empty] | 2019-12-22 | [6 empty] | 2019-12-29 | [6 empty] | 2020-01-05
No. | Tasks | PIC | Indicator | From | To | 0% | [6 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 |  | 1
[7 empty] | 2019-12-15 | 2019-12-16 | 2019-12-17 | 2019-12-18 | 2019-12-19 | 2019-12-20 | 2019-12-21 | 2019-12-22 | 2019-12-23 | 2019-12-24 | 2019-12-25 | 2019-12-26 | 2019-12-27 | 2019-12-28 | 2019-12-29 | 2019-12-30 | 2019-12-31 | 2020-01-01 | 2020-01-02 | 2020-01-03 | 2020-01-04 | 2020-01-05 | 2020-01-06 | 2020-01-07 | 2020-01-08 | 2020-01-09 | 2020-01-10 | 2020-01-11
1 | Biometrics - Christmas Party |  |  |  |  | 0% | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830 | 43831 | 43832 | 43833 | 43834 | 43835 | 43836 | 43837 | 43838 | 43839 | 43840 | 43841
1.1 | Change to Biometrics time to 4PM @ 1400 | Mec | 1 | 2019-12-21 | 2019-12-21 |  | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830 | 43831 | 43832 | 43833 | 43834 | 43835 | 43836 | 43837 | 43838 | 43839 | 43840 | 43841
|  | Von |  |  |  | 0% | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830 | 43831 | 43832 | 43833 | 43834 | 43835 | 43836 | 43837 | 43838 | 43839 | 43840 | 43841
1.2 | Change to Biometrics back to 6PM @ 1800 | Mec | 1 | 2019-12-21 | 2019-12-21 |  | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830 | 43831 | 43832 | 43833 | 43834 | 43835 | 43836 | 43837 | 43838 | 43839 | 43840 | 43841
|  | Von |  |  |  | 0% | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830 | 43831 | 43832 | 43833 | 43834 | 43835 | 43836 | 43837 | 43838 | 43839 | 43840 | 43841
2 | Production Schedule |  |  |  |  | 0% | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830 | 43831 | 43832 | 43833 | 43834 | 43835 | 43836 | 43837 | 43838 | 43839 | 43840 | 43841
2.1 | Printer Division Operation |  | 1 |  |  |  | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830 | 43831 | 43832 | 43833 | 43834 | 43835 | 43836 | 43837 | 43838 | 43839 | 43840 | 43841
[6 empty] | 0% | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830 | 43831 | 43832 | 43833 | 43834 | 43835 | 43836 | 43837 | 43838 | 43839 | 43840 | 43841
3 | HRC - W2 Processing (Tax) |  |  |  |  | 0% | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830 | 43831 | 43832 | 43833 | 43834 | 43835 | 43836 | 43837 | 43838 | 43839 | 43840 | 43841
3.1 | Restore Live Env Backup to Test Env | Aldrin | 1 | 2019-12-27 | 2019-12-27 |  | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830 | 43831 | 43832 | 43833 | 43834 | 43835 | 43836 | 43837 | 43838 | 43839 | 43840 | 43841
[6 empty] | 0% | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830 | 43831 | 43832 | 43833 | 43834 | 43835 | 43836 | 43837 | 43838 | 43839 | 43840 | 43841
3.2 | W2 Processing (Day 1) | Eye | 1 | 2019-12-27 | 2019-12-27 |  | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830 | 43831 | 43832 | 43833 | 43834 | 43835 | 43836 | 43837 | 43838 | 43839 | 43840 | 43841
|  | Aldrin |  |  |  | 0% | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830 | 43831 | 43832 | 43833 | 43834 | 43835 | 43836 | 43837 | 43838 | 43839 | 43840 | 43841
3.3 | W2 Processing (Day 2) | Eye | 1 | 2019-12-28 | 2019-12-28 |  | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830 | 43831 | 43832 | 43833 | 43834 | 43835 | 43836 | 43837 | 43838 | 43839 | 43840 | 43841
| (if cannot finish on Day 1) | Aldrin |  |  |  | 0% | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830 | 43831 | 43832 | 43833 | 43834 | 43835 | 43836 | 43837 | 43838 | 43839 | 43840 | 43841
3.4 | Tax Levelling and Checking | Eye | 1 | 2019-12-30 | 2019-12-30 |  | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830 | 43831 | 43832 | 43833 | 43834 | 43835 | 43836 | 43837 | 43838 | 43839 | 43840 | 43841
|  | Niña |  |  |  | 0% | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830 | 43831 | 43832 | 43833 | 43834 | 43835 | 43836 | 43837 | 43838 | 43839 | 43840 | 43841
4 | Canteen Activity |  |  |  |  | 0% | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830 | 43831 | 43832 | 43833 | 43834 | 43835 | 43836 | 43837 | 43838 | 43839 | 43840 | 43841
4.1 | Configure IP Address of 3 PCs | Aldrin | 1 | 2019-12-30 | 2019-12-30 |  | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830 | 43831 | 43832 | 43833 | 43834 | 43835 | 43836 | 43837 | 43838 | 43839 | 43840 | 43841
[6 empty] | 0% | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830 | 43831 | 43832 | 43833 | 43834 | 43835 | 43836 | 43837 | 43838 | 43839 | 43840 | 43841
4.2 | Register in ADMIN System - Canteen PC Master | Aldrin | 1 | 2019-12-30 | 2019-12-30 |  | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830 | 43831 | 43832 | 43833 | 43834 | 43835 | 43836 | 43837 | 43838 | 43839 | 43840 | 43841
[6 empty] | 0% | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830 | 43831 | 43832 | 43833 | 43834 | 43835 | 43836 | 43837 | 43838 | 43839 | 43840 | 43841
4.3 | Testing of Canteen Station PCs | Aldrin | 1 | 2019-12-30 | 2019-12-30 |  | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830 | 43831 | 43832 | 43833 | 43834 | 43835 | 43836 | 43837 | 43838 | 43839 | 43840 | 43841
[6 empty] | 0% | 43814 | 43815 | 43816 | 43817 | 43818 | 43819 | 43820 | 43821 | 43822 | 43823 | 43824 | 43825 | 43826 | 43827 | 43828 | 43829 | 43830 | 43831 | 43832 | 43833 | 43834 | 43835 | 43836 | 43837 | 43838 | 43839 | 43840 | 43841
Delayed
On-Schedule
Finished but delayed
Note on H7: Input base sunday